## Sheet1
Review Log
ID | Document ID | Document Version | Owner | Reviewer | Status | Comment | Review Date | Resolver | Resolving Date | Review Status
REV_001 | Review Log | v1.0 | Technical/Testing team | Ramadan | Not completed | There is no review comments; that mean you didn't do any reviews yet on delivered documents, although there is 'Reviewer' in most of delivered documents |  | Technical/Testing team | 14/4/2018 | Resolved/Closed
REV_002 | CONFG_PLN | v1.0 | Technical/Testing team | Ramadan | Not completed | Team didn't follow naming convntion you mention in section 3.3.1 in document convention part |  | Marwan Thabet | 13/4/2018 | Resolved/Closed
REV_003 | CONFG_PLN | v1.0 | Technical/Testing team | Ramadan | Not Clear | Branching approach not clear enough in CM plan |  | Marwan Thabet | 13/4/2018 | Resolved/Closed
REV_004 | RTM | v1.0 |  | Ramadan | Not completed | SRS, SIQ and test cases IDs not included in RTM sheet |  | Khaled Hossam, Basma Karama | 14/4/2018 | Resolved/Closed
REV_005 | SRS | v1.0 | Technical team | Ramadan | Not Clear | SRS IDs not cleat enough; you have just write CRS ids inside it. You have to translate/convert CRS to technical SRS and give every requirement in SRS an ID |  | Khaled Hossam, Basma Karama, Esraa Ahmed | 14/4/2018 | Resolved/Closed
REV_006 | SYS_TST_CAS | v1.0 | Testing team | Ramadan | Not Clear | TC_1, need to clarify which scenario you want to validate; as validate happy scenario is vast, so you need to specify it clearly. This comment apply for all the same test cases; I just took an example |  | Basma Karama, Esraa Ahmed | 13/4/2018 | Resolved/Closed
REV_007 | TEST_PLN | v1.0 | Testing team | Eng. Mohamed Hassan | Not Clear | Items Not to be Tested,Features not to be tested, Need to be removed because they are not in the project scope | 14/4/2018 | Soha Swailem | 15/4/2018 | Resolved/Closed
REV_008 | TEST_PLN | v1.0 | Testing team | Eng. Mohamed Hassan | Not Clear | Review strategy need to be included for the items need to be tested | 14/4/2018
REV_009 | TEST_PLN | v1.0 | Testing team | Eng. Mohamed Hassan | Not Clear | Regression Test Need To be more Clarified | 14/4/2018 | Soha Swailem | 15/4/2018 | Resolved/Closed
REV_010 | TEST_PLN | v1.1 | Testing team | Eng. Mohamed Hassan | Not Clear | Severity Criteria need to be defined | 14/4/2018
REV_011 | SRS | v1.0 | Technical Team | Basma | Not Clear | 1- The Motor Driver as per requirement from the customer should be included in SRS 2- The Short, Long and frequent press should be cleared in SRS 3- "Motor rotational speed will be evaluated based on sight and sound as per requested by the customer" should be included in SRS | 16/4/2018 | khaled hossam | 17/4/2018 | Resolved/Closed
REV_012 | HLD | v1.0 | Technical Team | Abd-Elrahman | Not Clear | 1-API's naming convention not followed as in naming convention doucment | 2018-04-16 | Muhammad Elzeiny | 19/4/2018 | Resolved/Closed
| TEST_PLN => Criteria for determining severity | v1.0 | Testing team | Marwan Ahmed | Not Clear | 1- The document title should be more descriptive please make it "Criteria for determining severity" instead of "Severity" 2- The mentioned Criteria are general please make them more specific and related to our project
| Project Milesontes | v1.0 | Testing team | Marwan Ahmed | Not Clear | RTM should be in a separate task not connected to Design document so make a task card for RTM and another two cards for high level design and component design documents
| SRS | v1.0 | Testing team | Basma and Ahmed Raafat | Not Clear | 1- [SRS _9] Frequent button press is described as button pressing and releasing in interval less than 1/3 second. It should mention what will be happened 2- [SRS _4] Motor operating voltage is between 5 to 9V. It should specify that the motor will work in this range only otherwise it will be off 3- Feature 2: Power supply should be connected to the motor to provide voltage either inside or outside the voltage range. ower supply should be connected to the motor driver not motor directly. 4- Feature 2: The SIQ suggested using fuse to control the overvoltage state instead of the HW protection circuit. 5- Feature2: You can’t assume that the motor voltage is stable and it should be protected also by a fuse as stated in SIQ updates, also don’t use the term hw protection circuit as it may be fuse. | 18/4/2018
REV_15 | all CDD documents | v1.0 | Technical team | Abd-Elrahman | Not Clear | all CDD doucuments should be named as in HLD | 19/4/218 | Abd-Elrahman | 2018-04-19 | Resolved/Closed
REV_16 | HLD_7 | v1.0 | Technical team | Abd-Elrahman | Not completed | 1/review history is empty 2/all service ID and Req ID are empty 3/interfaces(services) has no description 4/naming convention not met | 19/4/218 | Abd-Elrahman | 2018-04-19 | Resolved/Closed