## Sheet1
Review Log
ID | Document ID | Document Version | Owner | Reviewer | Status | Comment | Review Date | Resolver | Resolving Date | Review Status
REV_001 | Review Log | v1.0 | Technical/Testing team | Ramadan | Not completed | There is no review comments; that mean you didn't do any reviews yet on delivered documents, although there is 'Reviewer' in most of delivered documents |  | Technical/Testing team | 14/4/2018 | Resolved/Closed
REV_002 | CONFG_PLN | v1.0 | Technical/Testing team | Ramadan | Not completed | Team didn't follow naming convntion you mention in section 3.3.1 in document convention part |  | Marwan Thabet | 13/4/2018 | Resolved/Closed
REV_003 | CONFG_PLN | v1.0 | Technical/Testing team | Ramadan | Not Clear | Branching approach not clear enough in CM plan |  | Marwan Thabet | 13/4/2018 | Resolved/Closed
REV_004 | RTM | v1.0 |  | Ramadan | Not completed | SRS, SIQ and test cases IDs not included in RTM sheet |  | Khaled Hossam, Basma Karama | 14/4/2018 | Resolved/Closed
REV_005 | SRS | v1.0 | Technical team | Ramadan | Not Clear | SRS IDs not cleat enough; you have just write CRS ids inside it. You have to translate/convert CRS to technical SRS and give every requirement in SRS an ID |  | Khaled Hossam, Basma Karama, Esraa Ahmed | 14/4/2018 | Resolved/Closed
REV_006 | SYS_TST_CAS | v1.0 | Testing team | Ramadan | Not Clear | TC_1, need to clarify which scenario you want to validate; as validate happy scenario is vast, so you need to specify it clearly. This comment apply for all the same test cases; I just took an example |  | Basma Karama, Esraa Ahmed | 13/4/2018 | Resolved/Closed
REV_007 | TEST_PLN | v1.0 | Testing team | Eng. Mohamed Hassan | Not Clear | Items Not to be Tested,Features not to be tested, Need to be removed because they are not in the project scope | 14/4/2018 | Soha Swailem | 15/4/2018 | Resolved/Closed
REV_008 | TEST_PLN | v1.0 | Testing team | Eng. Mohamed Hassan | Not Clear | Review strategy need to be included for the items need to be tested | 14/4/2018
REV_009 | TEST_PLN | v1.0 | Testing team | Eng. Mohamed Hassan | Not Clear | Regression Test Need To be more Clarified | 14/4/2018 | Soha Swailem | 15/4/2018 | Resolved/Closed
REV_010 | TEST_PLN | v1.1 | Testing team | Eng. Mohamed Hassan | Not Clear | Severity Criteria need to be defined | 14/4/2018
REV_011 | SRS | v1.1 | Technical Team | Basma | Not Clear | 1- The Motor Driver as per requirement from the customer should be included in SRS 2- The Short, Long and frequent press should be cleared in SRS 3- "Motor rotational speed will be evaluated based on sight and sound as per requested by the customer" should be included in SRS | 16/4/2018
REV_012 | HLD | v1.0 | Technical Team | Abd-Elrahman | Not Clear | 1-API's naming convention not followed as in naming convention doucment | 2018-04-16