## Sheet1
Risk Management Plan
Project Name: Kenovo_Blender |  |  |  | Response Type: | Probability: | Impact: | Priority Score=Risk Probability X Risk Impact
|  |  |  | Avoid | 5> 75% | 5=Critical
|  |  |  | Transfer | 4> 50% | 4=Severe
|  |  |  | Mitigate | 3> 25% | 3=Major
|  |  |  | Accept | 2> 10% | 2=Moderate
[5 empty] | 1> 0% | 1=Minor
ID | Who | When | What |  |  |  | Who | What | How
# | Who Identified | Date Identified | Risk Description | Probability | Impact | Priority Score | Owner | Response Type | Response Plan
RIS_1 | Salma Abo kamla Basma Emad Karama | 2018-03-31 | Project schedule deviation | 3 | 4 | 12 | project team member | Mitigate | Distribute tasks between available resources with overtime to meet the deadline.
RIS_2 |  |  | Ambiguous requirements | 3 | 4 | 12 |  | Mitigate | The customer involvement as possible as we can.
RIS_3 |  |  | Designed skipped or created after code is written | 1 | 3 | 3 |  | Avoid | Priories all the written documentation before coding.
RIS_4 |  |  | Inconsistent coding style | 1 | 2 | 2 |  | Avoid | Follow one of the standard of coding style.
RIS_5 |  |  | No real time schedule analysis | 3 | 4 | 12 |  | Mitigate | Focus on the basic functionality of the system.
RIS_6 |  |  | Requirements aren't fully coverage | 2 | 4 | 8 |  | Avoid | Peer review after finishing any test phase and making sure all requirements are traceable to specific test cases.
RIS_7 |  |  | Insufficient consideration of safety | 2 | 5 | 10 |  | Avoid | Execute stress testing and load testing.
RIS_8 |  |  | Lesson learned not being recorded | 2 | 3 | 6 |  | Accept
RIS_9 |  |  | Tools are malfunctioned | 2 | 3 | 6 |  | Avoid | Make a well detailed business plan include budget and the specification of the tools.
RIS_10 |  |  | Resources absent | 2 | 4 | 8 |  | Mitigate | Distribute tasks between available resources with overtime to meet the deadline.
RIS_11 |  |  | Customer consultation delay | 3 | 4 | 12 |  | Avoid | Project will proceed with pre assumed requirements.
RIS_12 |  |  | Sudden change in requirements | 3 | 4 | 12 |  | Accept
RIS_13 |  |  | Technical risks (Design tradeoff) | 2 | 3 | 6 |  | Avoid | More project focus on designing and architecting before proceeding with implementation.
RIS_14 |  |  | Conflicts between team members | 2 | 4 | 8 |  | Mitigate | Take action and help them resolve the situation before it spirals out of control.
RIS_15 |  |  | Inadequate estimation of code size and effort | 2 | 3 | 6 |  | Transfer | Delegate someone to monitor deadline of each tasks and progress.
RIS_16 |  |  | Project milestones are not clearly defined | 2 | 4 | 8 |  | Avoid | Periodic meetings to set and clarify project objectives and progress.
RIS_17 |  |  | Misunderstanding of the requirements | 2 | 4 | 8 |  | Avoid | The customer involvement as possible as we can.