## Sheet1
Review Log
ID | Document ID | Document Version | Owner | Reviewer | Status | Comment | Review Date | Resolver | Resolving Date | Review Status
REV_001 | Review Log |  | Technical/Testing team | Ramadan | Not completed | There is no review comments; that mean you didn't do any reviews yet on delivered documents, although there is 'Reviewer' in most of delivered documents
REV_002 | CONFG_PLN |  | Technical/Testing team | Ramadan | Not completed | Team didn't follow naming convntion you mention in section 3.3.1 in document convention part
REV_003 | CONFG_PLN |  | Technical/Testing team | Ramadan | Not Clear | Branching approach not clear enough in CM plan
REV_004 | RTM |  |  | Ramadan | Not completed | SRS, SIQ and test cases IDs not included in RTM sheet
REV_005 | SRS |  | Technical team | Ramadan | Not Clear | SRS IDs not cleat enough; you have just write CRS ids inside it. You have to translate/convert CRS to technical SRS and give every requirement in SRS an ID
REV_006 | SYS_TST_CAS |  | Testing team | Ramadan | Not Clear | TC_1, need to clarify which scenario you want to validate; as validate happy scenario is vast, so you need to specify it clearly. This comment apply for all the same test cases; I just took an example