## Sheet1
Project Scope
Key deliverables of this project:
1-SIQ
2-CRS
3-SRS
4-TEST Plan Document
5-Project Plan Document
6-Test cases
7-Review log
8-Working prototype
9-Desing Document
Functionality in scope:
1- Electric blender with 3 speeds. 2- Hardware protection circuit for over-voltage detection, In case of over-voltage detection the system shuts down completely. 3- The blender have 4 operating states in sequence controlled using one tactile button (off >> speed 1 >> speed 2 >> speed 3). 4- Motor will rotate in clock wise direction. 5- The voltage monitoring is for the motor supply voltage not the mc supply voltage. 6- Voltage detection circuit should be connected to the motor supply voltage. 7- Additional hardware can be used to detect the over-voltage state. 8- A recovery feature to stop the motor If the voltage exceeds motor operating voltage. 9- the speeds percentage from maximum speed: • speed 1 = speed/3 • speed 2 = speed/3 + speed 1 • speed 3 = speed/3 + speed 2 10- Speed remains the same if user pressed button forever. Blender stays active with current speed unless user changes its operating state using button. 11- Button used is tactile switch. 12- Action is immediately taken after button release with no delays. 13- Must press button and release it to initiate action. 14- The action is supposed to be initiated in no time from the request time at button release. 15- The motor should be supplied the sufficient voltage for optimum operating conditions. 16- The motor driver circuit must be isolated from the control circuit to avoid reflected current from burning the controller. 17- Motor must be isolated in a chase to protect the user from touching the blades.
Functionality out of scope:
1- ON/OFF switch to control Kenovo_ElectricBlender. 2- Move direct from off state to higher speed (two or three). 3- LCD to display the speed of Kenovo_ElectricBlender. 4- LCD to display the supplying voltage to Kenovo_ElectricBlender. 5- Kenovo_ElectricBlender support two direction of the motor (forward-reverse). 6- KEYPAD to choose between different speeds 7- Motor should remain ON in case of over-voltage condition. 8- Speed of the motor change if user pressed button forever. 9- Time delay to initiate the Action after user releases the button